## Objectives
Cuckfield Council Strategic Objectives
1 | Reflect the benefit to Cuckfield in all council operations
2 | Efficient delivery of services. Responsible budgetary and financial control
3 | Improving community engagement and public profile
4 | Increasing sustainability and environmental enhancement in council operations and projects
5 | Maintaining the character and distinctiveness of the village
6 | Maintaining and improving community assets for the enjoyment of all residents
7 | Improving safety and reduction of noise on village highways

## Activities
[7 empty] | 15 | 29 | 27 | 20 | 15
Ref | Activity Desciption | Committee Lead | Maintenance / Project | Estimated costs | Collaboration funding | % complete | 2023 | 2024 | 2025 | 2026 | 2027 | Jan 26 review
1 | Co-ordinate annual parish roadshow meeting with other organisations | Council | Maintenance | Low | Precept - Maintenance
2 | Increased police presence in village | Council | Maintenance | Low | None
3 | Investigate further local council collaboration | Council | Maintenance | None | Precept - Maintenance
4 | Finance Twittens lighting | Council | Maintenance | Medium | Precept - Maintenance
5 | Enhanced sustainability policies recognising climate change | Council | Project | Low | Precept - Maintenance |  |  | 1 | 1 |  |  | K
6 | Extend CPC recycling, including recyling scheme | Council | Project | Low | Precept - Maintenance |  |  | 1 | 1 |  |  | K
7 | Implement Parish communications strategy | Council | Project | Low | Precept - Maintenance |  | 1 | 1 | 1 | 1 | 1 | K
8 | Cuckfield Local market attendance | Council | Project | None | None |  | 1 | 1 | 1 | 1 | 1 | J
9 | Produce and sell Cuckfield calendar | Council | Project | Low | None |  | 1 | 1 | 1 | 1 | 1 | K
10 | Run additional community events | Council | Project | Medium | Precept - Major project |  | 1 | 1 | 1 |  | 1 | J
11 | Further engagement with elderly residents | Council | Project | Low | Precept - Minor project |  | 1 | 1 | 1 |  | 1 | J
12 | Mobile phone coverage improvements | Council | Project | Low | To be identified |  |  | 1 | 1 |  |  | K
13 | Reinstate Post Office in Cuckfield | Council | Project | Low | Precept - Minor project |  | 1 | 1 |  |  |  | L
14 | Launch 'what's on' websites | Council | Project | Low | Precept - Minor project |  |  | 1 |  |  |  | K
15 | Investigate setting up Cuckfield Repair Shop | Council | Project | Medium | Precept - Minor project |  |  |  | 1 | 1 | 1 | K
16 | Change of name to Cuckfield Council | Council | Project | Low | Precept - Minor project |  |  | 1 |  |  |  | L
17 | Produce and distribute food parcels twice a year to those in need | Council | Project | Medium | Precept - Minor project |  | 1 | 1 | 1 | 1 | 1 | J
18 | Cemetery maintenance | Assets Community Environment | Maintenance | Medium | Precept - Maintenance
19 | Regular cleaning of bus shelters | Assets Community Environment | Maintenance | Low | Precept - Maintenance
20 | Twittens maintenance | Assets Community Environment | Maintenance | Low | Precept - Maintenance
21 | Allottments management | Assets Community Environment | Maintenance | Low | Precept - Maintenance
22 | Public toilets maintenance | Assets Community Environment | Maintenance | Medium | Precept - Maintenance
23 | Maintenance of skateboard park | Assets Community Environment | Maintenance | Low | Precept - Maintenance
24 | Support additional theatre shows | Assets Community Environment | Project | Low | Precept - Minor project |  |  | 1 | 1 | 1 | 1 | J
25 | Tourism marketing plan | Assets Community Environment | Project | Low | Precept - Minor project |  |  | 1 |  |  |  | L
26 | “Historic Cuckfield” Tourist signs on the A272 | Assets Community Environment | Project | Low | Precept - Minor project |  |  | 1 |  |  |  | L
27 | Cemetery extension | Assets Community Environment | Project | High | Loan |  |  |  | 1 |  |  | L
28 | Aquire Buttinghill Drive public open space | Assets Community Environment | Project | None | Section 106 |  | 1 | 1 |  |  |  | L
29 | Implement Buttinghill Drive open space landscape plan | Assets Community Environment | Project | Medium | Section 106 |  |  | 1 | 1 |  |  | L
30 | Expansion of Worsley Memorial Ground parking | Assets Community Environment | Project | Low | Section 106 |  |  |  | 1 |  |  | L
31 | Children's play equipment at Whiteman's Green fields | Assets Community Environment | Project | Medium | Section 106 |  |  |  |  | 1 |  | L
32 | Take over Glebe Road allotments from Mid Sussex District Council | Assets Community Environment | Project | Medium | Grants & awards |  |  |  |  | 1 |  | L
33 | BMX track at Whiteman's Green | Assets Community Environment | Project | Medium | Grants & awards |  |  |  |  | 1 |  | L
34 | Improve relationship with village retail sector | Assets Community Environment | Project | Low | Precept - Minor project |  | 1 | 1 | 1 |  |  | K
35 | Additional summer and winter community events | Assets Community Environment | Project | Medium | Precept - Minor project |  | 1 | 1 | 1 | 1 | 1 | J
36 | Increase verge wildflower areas | Assets Community Environment | Project | Medium | Precept - Minor project |  |  | 1 | 1 |  |  | J
37 | Welcome to Cuckfield initiative with local Estate Agents | Assets Community Environment | Project | Low | Precept - Minor project |  |  | 1 |  |  |  | L
38 | Annual tidy-up community event | Assets Community Environment | Project | Low | Precept - Minor project |  |  |  | 1 | 1 | 1 | J
40 | Effective Queens Hall/Village Hall management and maintenance | Community Buildings | Maintenance | High | Precept - Maintenance
39 | Queens Hall garden improvements | Community Buildings | Project | Medium | Precept - Major project |  | 1 | 1 |  |  |  | J
41 | Village Hall strategy progression and funding | Community Buildings | Project | High | Grants & awards |  |  | 1 |  |  |  | K
42 | Art exhibition in QH foyer | Community Buildings | Project | None | Precept - Minor project |  | 1 | 1 | 1 | 1 |  | J
43 | Planning application timely recommendations to MSDC | Planning | Maintenance | Low | Precept - Maintenance
44 | Neighbourhood Plan monitoring | Planning | Maintenance | Low | Precept - Maintenance
45 | Extension of Blunts Wood/Paiges Meadow LNR into the Borde Hill Millennium Forest | Planning | Project | Low | Precept - Minor project |  |  |  | 1 |  |  | L
46 | Continue to resist planning applications which do not meet Neighbourhood Plan policies | Planning | Project | Medium | Precept - Minor project |  | 1 | 1 | 1 | 1 | 1 | J
47 | Neighbourhood Plan Review | Planning | Project | High | Precept - Major project |  | 1 | 1 | 1 |  |  | K
48 | Road signage cleaning | Roads and Traffic | Maintenance | Low | Precept - Maintenance
49 | Continue supporting Speedwatch | Roads and Traffic | Maintenance | Low | Precept - Maintenance
50 | Conversion of Ardinlgly Road zebra crossings to puffins | Roads and Traffic | Project | High | Section 106 |  |  |  |  | 1 | 1 | L
51 | Implementation of further traffic calming measures | Roads and Traffic | Project | High | Precept - Minor project |  |  |  |  | 1 | 1 | L
52 | Additional cycle parking facilities | Roads and Traffic | Project | Medium | Precept - Minor project |  |  |  | 1 |  |  | L
53 | Pedestrian crossing at Whitemans Green | Roads and Traffic | Project | High | Precept - Major project |  |  |  |  | 1 |  | L
54 | Traffic light management for speed control | Roads and Traffic | Project | High | Precept - Major project |  |  |  | 1 | 1 |  | L
55 | New bus shelter at Warden Court | Roads and Traffic | Project | Medium | Precept - Minor project |  |  | 1 |  |  |  | L
56 | Resolve parking disc issues | Roads and Traffic | Project | None | Precept - Minor project |  |  | 1 |  |  |  | L
57 | Collaborate to resolve Whitemans Green parking issues | Roads and Traffic | Project | Medium | To be identified |  |  |  | 1 |  |  | L
58 | SID data collation and assessment | Roads and Traffic | Project | Low | Precept - Minor project |  | 1 | 1 | 1 | 1 | 1 | J
59 | Install emissions monitoring bollards | Roads and Traffic | Project | High | Precept - Major project |  |  |  |  | 1 |  | L
60 | Implement 20mph zones through village | Roads and Traffic | Project | Medium | Precept - Major project |  |  |  | 1 | 1 | 1 | L