## Sheet1
[13 empty] | Grants & Awards |  | 250 | 4250 | 6250 | 11750 | 1250
[13 empty] | Loan |  | 0 | 20000 | 0 | 0 | 0
[13 empty] | Section 106 |  | 11000 | 75000 | 20000 | 50000 | 0
[13 empty] | None |  | 0 | 0 | 0 | 0 | 0
[13 empty] | To be identified |  | 0 | 0 | 0 | 0 | 0
[13 empty] | Subtotal |  | 0 | 0 | 0 | 0 | 0
[13 empty] | Precept - Maintenance |  | 0 | 0 | 0 | 0 | 0
[13 empty] | Precept - Major project |  | 65000 | 66000 | 104000 | 4000 | 4000
[13 empty] | Precept - Minor project |  | 10200 | 15950 | 3700 | 2200 | 2200
[13 empty] | Precept Subtotal |  | 0 | 0 | 0 | 0 | 0
[15 empty] | 86450 | 181200 | 133950 | 67950 | 7450 | 6 | 6 | 6 | 14 | 16 | 16 | 11 | 14 | 9 | 9 | 7 | 3 | 3 | 3 | 2 | 3 | 2 | 2
Ref | Activity Desciption | Location | Why? | Added | Committee | Short-Long objective | Maintenance / Project | Progress to short list? | Priority | Collaboration with | Specific actions | Ownership | Funding from | % complete | Costs Financial Year |  |  |  |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
|  | Where? | [12 empty] | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
1 | Co-ordinate annual parish meeting with other organisations | Village | Enhance community and meeting | 2019-07-01 | Council | Medium | Maintenance | Yes | High | Parish organisations | Contact organisations | Clerk | Precept - Maintenance | 50% | bar: 2020 Q4 to 2020 Q1; 2021 Q4 to 2021 Q1; 2022 Q4 to 2022 Q1; 2023 Q4 to 2023 Q1
2 | Sign a military covenant | Community | Support for armed services | 2019-07-01 | Council | Long | Project | No
3 | Enhanced environmental policy recognising climate change | Community | Public awareness of climate change | 2019-07-01 | Council | Medium | Project | Yes | High |  | Further discussion on implications | Clerk | Precept - Maintenance | 20% | bar: 2020 Q1 to 2022 Q4
4 | Convene a Parish Youth Council | Community | Engage younger people | 2019-07-01 | Council | Medium | Project | Yes | Medium | Warden Park | Working Party. Contact Warden Park | WP Chair | Precept - Minor project | 10% | Costs Financial Year 19/20: 200; Costs Financial Year 20/21: 200; Costs Financial Year 21/22: 200; Costs Financial Year 22/23: 200; Costs Financial Year 23/24: 200; 2020 Q1: 1; 2020 Q3: 1; 2021 Q1: 1; 2021 Q3: 1; 2022 Q1: 1; 2022 Q3: 1; 2023 Q1: 1
5 | Reinstigate youth club | Community | Activities for younger people | 2019-07-01 | Council | Medium | Project | Yes | Medium | Warden Park | Working Party. Contact Warden Park | WP Chair | Grants & awards | 10% | Costs Financial Year 20/21: 1000; Costs Financial Year 21/22: 1000; Costs Financial Year 22/23: 1000; Costs Financial Year 23/24: 1000; 2020 Q3: 1; 2021 Q4: 1; 2021 Q1: 1
6 | Develop a Parish communications strategy | CPC | Better communicate parish work to village | 2019-07-01 | Council | Short | Project | Yes | High | Consultant | Engage consultant to develop? | Chair | Precept - Minor project | 0% | Costs Financial Year 19/20: 2000; Costs Financial Year 20/21: 500; Costs Financial Year 21/22: 300; Costs Financial Year 22/23: 300; Costs Financial Year 23/24: 300; 2020 Q4: 1; 2020 Q1: 1
7 | Strategy for additional community events | Community | Enhance community & wellbeing | 2019-07-01 | Council | Medium | Project | Yes | Medium | Charity Sector | Working Party with CuckSoc, ISOC, Churches | WP Chair | Precept - Minor project | 20% | Costs Financial Year 19/20: 500; Costs Financial Year 20/21: 200; Costs Financial Year 21/22: 200; Costs Financial Year 22/23: 200; Costs Financial Year 23/24: 200; 2020 Q4: 1; 2020 Q1: 1; 2020 Q3: 1; 2021 Q4: 1; 2021 Q1: 1; 2021 Q2: 1; 2021 Q3: 1; 2022 Q4: 1
8 | Strategy for engagement with elderly residents | Community | Enhance community & wellbeing | 2019-07-01 | Council | Short | Project | Yes | High | Charity Sector | Schedule of events, with CuckSoc, ISOC, Churches | WP Chair | Grants & awards | 50% | Costs Financial Year 19/20: 250; Costs Financial Year 20/21: 250; Costs Financial Year 21/22: 250; Costs Financial Year 22/23: 250; Costs Financial Year 23/24: 250; 2019 Q2: 1; 2019 Q3: 1; 2020 Q4: 1; 2020 Q3: 1; 2021 Q3: 1; 2022 Q3: 1
9 | CPC recycling policy, including recyling scheme | Community | Enhance community & wellbeing | 2019-07-01 | Council | Medium | Project | Yes | High | TerraCycle. Self funding | Draw up recycling policy. Colin McFarlane | Clerk | None | 10% | bar: 2020 Q1 to 2022 Q4
10 | Mobile phone coverage improvements (incl smart meters) | Community | Enhance community & wellbeing | 2019-07-01 | Council | Long | Project | Yes | High | ? | Contact Ofcom & Ofgem | ? | To be identified | 0% | bar: Costs Financial Year 19/20; 2022 Q1 to 2023 Q3
11 | Increased police presence in village | Community | Anti-social behaviour mitigation | 2019-07-01 | Council | Short | Maintenance | Yes | Medium | Police Commissioner | Liaise with District Councillors and Police | Chair | None | 30% | bar: 2019 Q2 to 2020 Q3
12 | Action Plan to promote village economy | Village | Ensure a vibrant village | 2019-07-01 | F&GP | Short | Project | Yes | Medium | Shops | Set up Working Party | WP Chair | Precept - Minor project | 0% | Costs Financial Year 19/20: 2000; Costs Financial Year 20/21: 1000; Costs Financial Year 21/22: 500; Costs Financial Year 22/23: 500; Costs Financial Year 23/24: 500; 2019 Q2: 1; 2019 Q3: 1; 2020 Q4: 1; 2020 Q1: 1; 2020 Q2: 1
13 | Investigate further Partnership working enhancements | CPC | Savings with neighbouring councils | 2019-07-01 | F&GP | Short | Maintenance | Yes | High | HHTC, ASPC | Discuss with town & parish clerks | Clerk | Precept - Maintenance | 50% | bar: 2019 Q2 to 2020 Q1
14 | Twittens lighting | Highways | Community asset maintenance | 2019-07-01 | F&GP | On-going | Maintenance | Yes | High | WSCC Highways |  | Clerk | Precept - Maintenance | 100% | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
15 | Additional bus services | Community | Enhance community & wellbeing | 2019-07-01 | F&GP | Medium | Maintenance | No
16 | Parish digital file sharing | CPC | Efficient digital management | 2019-07-01 | F&GP | Short | Project | Yes | High |  | Set up | Clerk | Precept - Maintenance | 100% | bar: 2020 Q4
17 | Tourism marketing plan | Community | Enhance economic activity | 2019-07-01 | F&GP | Medium | Project | Yes | High | Consultant | Working Party to engage consultant | WP Chair | Precept - Major project | 0% | Costs Financial Year 20/21: 5000; Costs Financial Year 21/22: 1000; Costs Financial Year 22/23: 1000; Costs Financial Year 23/24: 1000; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1; 2021 Q1: 1; 2021 Q2: 1; 2021 Q3: 1; 2022 Q4: 1
18 | “Historic Cuckfield” Tourist signs on the A272 | Village | Enhance economic activity | 2019-07-01 | F&GP | Medium | Project | Yes | Medium | WSCC Highways | Tourism Working Party to review | WP Chair | Precept - Minor project | 0% | Costs Financial Year 20/21: 500; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1; 2021 Q1: 1; 2021 Q2: 1; 2021 Q3: 1; 2022 Q4: 1
19 | Reinstate Post Office in Cuckfield | Queens Hall | Enhance community & wellbeing | 2019-07-01 | F&GP | Short | Project | Yes | Medium | Post Office | Liaise with Post Office master | Clerk | Precept - Minor project | 100% | Costs Financial Year 19/20: 500; 2020 Q4: 1
20 | Cemetery maintenance | Cemetery | Community asset maintenance | 2019-07-01 | ACE | On-going | Maintenance | Yes | Medium |  |  | Clerk | Precept - Maintenance | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
21 | Cemetery future needs assessment | Cemetery | Remaining space limited | 2019-07-01 | ACE | Short | Maintenance | Yes | High |  | Investigate options | ACE Chair | Precept - Minor project | 50% | Costs Financial Year 19/20: 500; 2019 Q3: 1; 2020 Q4: 1
22 | Cemetry extension | Cemetery | Expand space available | 2019-07-01 | ACE | Long | Project | Yes | Medium | Landowner | Review options. Self financing in long run | ACE Chair | Loan | 20% | Costs Financial Year 20/21: 20000; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1; 2021 Q1: 1
23 | Open cemetery pathways repairs | Cemetery | Safety requirements | 2019-07-01 | ACE | Short | Maintenance | Yes | High | C of E | Construction commencement | ACE Chair | Precept - Major project | 100% | Costs Financial Year 19/20: 50000; 2019 Q2: 1; 2019 Q3: 1; 2020 Q4: 1
24 | Closed cemetery pathways replacement | Cemetery | Landscape enhancements | 2019-07-01 | ACE | Long | Maintenance | Yes | Medium | C of E | Quotes to be appraised | ACE Chair | Precept - Major project | 100% | Costs Financial Year 21/22: 20000; 2021 Q1: 1; 2021 Q2: 1; 2021 Q3: 1; 2022 Q4: 1
25 | Chuch lych gates condition survey | Cemetery | Maintenance of listed structures | 2019-07-01 | ACE | Short | Maintenance | Yes | High | C of E | Inspection surveys required | ACE Chair | Precept - Minor project | 100% | Costs Financial Year 19/20: 2000; 2019 Q2: 1; 2019 Q3: 1; 2020 Q4: 1
26 | Aquire Buttinghill Drive public open space | Buttinghill Drive | Enhance community asset | 2019-07-01 | ACE | Short | Project | Yes | High | Taylow Wimpey, MSDC | Continue to push MSDC | Chair | Section 106 | 0% | Costs Financial Year 19/20: 1000; 2020 Q4: 1
27 | Horsefield Green landscape plan completion | Horsefield Green | Enhance community asset | 2019-07-01 | ACE | Short | Maintenance | Yes | High |  | Implement plan | Clerk | Section 106 | 50% | Costs Financial Year 19/20: 10000; Costs Financial Year 20/21: 5000; 2020 Q4: 1; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1
28 | Obtain Village Green status for Horsefield/Buttinghill POS | Horsefield/Buttinghill | Enhance community asset | 2019-07-01 | ACE | Medium | Project | Yes | Medium | Defra | Apply to Defra | Chair | Precept - Minor project | 0% | Costs Financial Year 20/21: 300; 2021 Q4: 1; 2021 Q1: 1
29 | Implement Buttinghill Drive open space landscape plan | Buttinghill Drive | Enhance community asset | 2019-07-01 | ACE | Short | Maintenance | Yes | High |  | Implement plan | Clerk | Section 106 | 0% | Costs Financial Year 20/21: 10000; 2020 Q2: 1; 2020 Q3: 1
30 | Queens Hall roof condition survey | Queens Hall | Maintenance of listed structures | 2019-07-01 | ACE | Short | Maintenance | Yes | High |  | Inspection surveys required | Clerk | Precept - Minor project | 100% | Costs Financial Year 19/20: 500; 2019 Q2: 1; 2019 Q3: 1
31 | Queens Hall roof repairs | Queens Hall | Maintenance of listed structures | 2019-07-01 | ACE | Medium | Maintenance | Yes | Medium |  | Review options | ACE Chair | Precept - Major project | 100% | Costs Financial Year 20/21: 50000; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1
32 | Queens Hall gardens enhancements | Queens Hall | Following extension into adjacent property | 2019-07-01 | ACE | Medium | Project | Yes | Medium |  | ACE committee to review options | ACE Chair | Precept - Minor project | 50% | Costs Financial Year 19/20: 2000; 2019 Q2: 1
33 | Queens Hall/Village Hall management | Village Hall | Community asset maintenance | 2019-07-01 | ACE | On-going | Maintenance | Yes | High |  |  | Clerk | Precept - Maintenance | 100% | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
34 | Queens Hall garden extention to adjacent property | Queens Hall | Enhance community asset | 2019-07-01 | ACE | Short | Project | Yes | High | Land-owner | Landscape plan | WP Chair | Precept - Major project | 75% | Costs Financial Year 19/20: 10000; Costs Financial Year 20/21: 3000; Costs Financial Year 21/22: 3000; Costs Financial Year 22/23: 3000; Costs Financial Year 23/24: 3000; 2019 Q2: 1; 2019 Q3: 1; 2020 Q4: 1
35 | Replace Queens Hall proscenium arch (curtains) | Queens Hall | Existing fabric is worn | 2019-07-01 | ACE | Short | Maintenance | Yes | Medium | CDS | Lottery grant. Martin to review options | ACE Chair | Grants & awards | 0% | Costs Financial Year 20/21: 3000; 2020 Q1: 1
36 | Village Hall facility future options | Village Hall | Best use of asset and investment | 2019-07-01 | ACE | Short | Project | Yes | Medium | Architect | Set up working party | WP Chair | Precept - Minor project | 20% | Costs Financial Year 20/21: 3000; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1; 2021 Q1: 1
37 | Regular cleaning of bus shelters | Highways | Village tidiness | 2019-07-01 | ACE | On-going | Maintenance | Yes | High | Bus company | Add to duties of village orderly | Clerk | Precept - Maintenance | 100% | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
38 | More benches throughout village | Community | Enhance community & wellbeing | 2019-07-01 | ACE | Medium | Project | Yes | Medium |  | AONB grant. ACE committee to review options | ACE Chair | Grants & awards | 0% | Costs Financial Year 21/22: 3000; 2021 Q1: 1; 2021 Q2: 1; 2021 Q3: 1; 2022 Q4: 1
39 | Twittens maintenance | Highways | Village tidiness | 2019-07-01 | ACE | On-going | Maintenance | Yes | High | HHTC |  | Clerk | Precept - Maintenance | 100% | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
40 | Allottments management | Allottments | Community asset maintenance | 2019-07-01 | ACE | On-going | Maintenance | Yes | High |  |  | Clerk | Precept - Maintenance | 100% | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
41 | Public toilets maintenance | Village | Community asset maintenance | 2019-07-01 | ACE | On-going | Maintenance | Yes | High |  |  | Clerk | Precept - Maintenance | 100% | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
42 | Determine landscape/maintenance plan for observer field | Observer field | Enhance community asset | 2019-07-01 | ACE | Medium | Maintenance | Yes | Medium | Landscaper | Engage landscaper (Bradley Woodward?) | ACE Chair | None | 100% | bar: 2020 Q1 to 2020 Q3
43 | Community asset management approach | Community | Efficient digital management of assets | 2019-07-01 | ACE | Medium | Project | Yes | Medium |  | PC office to review Parish On-line | Clerk | Precept - Minor project | 0% | Costs Financial Year 20/21: 250; 2020 Q2: 1; 2020 Q3: 1
44 | Install Community Orchard | Community | Enhance community & wellbeing | 2019-07-01 | ACE | Long | Project | Yes | Medium |  | AONB funding. ACE cttee to consider locations | ACE Chair | Grants & awards | 50% | Costs Financial Year 22/23: 500; 2022 Q2: 1; 2022 Q3: 1
45 | Expansion of Worsely Memorial Ground parking | Rec | Enhance community asset | 2019-07-01 | ACE | Medium | Project | Yes | Medium | MSDC | Further discussion with MSDC | ACE Chair | Section 106 | 0% | Costs Financial Year 21/22: 20000; 2021 Q1: 1; 2021 Q2: 1; 2021 Q3: 1
46 | Children's play equipment at Whiteman's Green fields | Whitemans Green | Enhance community & wellbeing | 2019-07-01 | ACE | Medium | Project | Yes | Medium | MSDC | ACE cttee to consider options | ACE Chair | Section 106 | 0% | Costs Financial Year 20/21: 15000; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1; 2021 Q1: 1
47 | Investment in Worsley Memorial Ground pavilion | Rec | Enhance community asset | 2019-07-01 | ACE | Long | Project | Yes | Medium | MSDC | PC to discuss viability with MSDC | Clerk | Section 106 | 0% | Costs Financial Year 22/23: 50000; 2022 Q1: 1; 2022 Q2: 1; 2022 Q3: 1; 2023 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 1
48 | Take over Glebe road allotments from Mid Sussex | Glebe Road | Enhance community asset | 2019-07-01 | ACE | Long | Project | Yes | Medium | MSDC | PC to discuss viability with MSDC | Clerk | Grants & awards | 0% | Costs Financial Year 21/22: 2000; 2021 Q2: 1; 2021 Q3: 1
49 | Additional bus services | Community | Enhance community & wellbeing | 2019-07-01 | ACE | Medium | Maintenance | No
50 | Digital real-time bus signage | Village | Increased use of public transport | 2019-07-01 | ACE | Short | Project | Yes | High | Bus provider | Pursue bus provider | Clerk | Section 106 | 50% | Costs Financial Year 20/21: 30000; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1
51 | Maintenance of skateboard park | Whitemans Green | Community asset maintenance | 2019-07-01 | ACE | On-going | Maintenance | Yes | High |  | Regular inspection | Clerk | Precept - Minor project | 100% | Costs Financial Year 20/21: 1000; Costs Financial Year 21/22: 1000; Costs Financial Year 22/23: 1000; Costs Financial Year 23/24: 1000; 2020 Q1: 1; 2021 Q1: 1; 2022 Q1: 1; 2023 Q1: 1
52 | BMX track at Whiteman's Green | Whitemans Green | Activities for younger people | 2019-07-01 | ACE | Medium | Project | Yes | Low | MSDC | Discuss with MSDC/Fairfax from ¦Rugby club development | ACE Chair | Grants & awards | 0% | Costs Financial Year 22/23: 10000; 2022 Q1: 1; 2022 Q2: 1; 2022 Q3: 1; 2023 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 1
53 | Works to Lychgates | Cemetery | Community asset maintenance | 2019-07-01 | ACE | Medium | Maintenance | Yes | High |  | Act on feedback from surveys | ACE Chair | Precept - Major project | 0% | Costs Financial Year 21/22: 20000; 2021 Q1: 1
54 | Queens Hall decoration | Queens Hall | Community asset maintenance | 2019-07-01 | ACE | Medium | Project | Yes | Medium |  | Obtain quotes | Clerk | Precept - Minor project | 100% | Costs Financial Year 20/21: 4000; 2020 Q1: 1
55 | Publish Parish Housing Land Availability Assessment update | Community | Development control & environment | 2019-07-01 | Planning | Short | Project | Yes | High |  | Update PHLAA assessment | Planning Chair | None | 100% | bar: 2019 Q2
56 | Review and respond to MSDC SHELAA when published | Community | Development control & environment | 2019-07-01 | Planning | Short | Project | Yes | High | Planning consultant | Engage planning consultant | Planning Chair | Precept - Major project | 100% | Costs Financial Year 19/20: 5000; 2019 Q3: 1
57 | Planning application timely recommendations to MSDC | Community | Development control & environment | 2019-07-01 | Planning | On-going | Maintenance | Yes | High |  |  | Clerk | Precept - Maintenance | 100% | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
58 | Neighbourhood Plan monitoring | Community | Development control & environment | 2019-07-01 | Planning | On-going | Maintenance | Yes | High |  |  | Clerk | Precept - Maintenance | 100% | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
59 | Contribution to a new wildlife education facility at the Court Meadow School site | Blunts Wood | Increse environmental education | 2019-07-01 | Planning | Medium | Project | Yes | Medium | Sussex Wildlife Trust | Working Party. Discuss with WSCC and SWT | WP Chair | Grants & awards | 10% | bar: Costs Financial Year 20/21 to Costs Financial Year 21/22; 2020 Q1 to 2022 Q4
60 | Extension of Blunts Wood/Paiges Meadow LNR into the Borde Hill Millennium Forest | Blunts Wood | Safeguard landscape characteristics | 2019-07-01 | Planning | Medium | Project | Yes | Low | Borde Hill | Write to Borde Hill | Planning Chair | Precept - Minor project | 10% | Costs Financial Year 20/21: 500; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1; 2021 Q1: 1; 2021 Q2: 1; 2021 Q3: 1; 2022 Q4: 1
61 | Conversion of AR zebra crossings to puffins | Ardingly Road | Additional pedestrian safety | 2019-07-01 | R&T | Medium | Project | Yes | Medium | WSCC Highways | Discuss with WSCC Highways | R&T Chair | Precept - Major project | 0% | Costs Financial Year 21/22: 30000; 2021 Q1: 1; 2021 Q2: 1; 2021 Q3: 1; 2022 Q4: 1
62 | Double yellow lines at top of London Lane | London Lane | Reduce traffic congestion | 2019-07-01 | R&T | Medium | Project | No
63 | Further road layout improvements at Rose and Crown | London Road | Traffic congestion/speed/safety | 2019-07-01 | R&T | Long | Project | No
64 | Strategy for next generation of village-wide traffic calming measures | Highways | Response to further local development | 2019-07-01 | R&T | Short | Project | Yes | Medium | Highways consultant | Employ consultant to develop | R&T Chair | Precept - Minor project | 20% | Costs Financial Year 20/21: 3000; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1
65 | Further London Lane traffic calming | London Lane | Reduce traffic speed & increase safety | 2019-07-01 | R&T | Medium | Project | Yes | High | WSCC Highways | Discuss with WSCC Highways | R&T Chair | Section 106 | 50% | Costs Financial Year 20/21: 15000; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1
66 | Additional cycle parking facilities | Highways | Promote cycling & wellbeing | 2019-07-01 | R&T | Short | Project | Yes | Low |  | R&T to determine potential locations | R&T Chair | Precept - Minor project | 0% | Costs Financial Year 21/22: 1500; 2021 Q1: 1; 2021 Q2: 1; 2021 Q3: 1; 2022 Q4: 1
67 | Purchase and deploy additional Speed Information Device (SID) | Highways | Reduce traffic speed & increase safety | 2019-07-01 | R&T | Medium | Project | Yes | High |  | PC to purchase | Clerk | Precept - Major project | 100% | Costs Financial Year 20/21: 6000; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1
68 | Road signage cleaning | Highways | Village tidiness | 2019-07-01 | R&T | Short | Maintenance | Yes | High |  | Map of signs to clean. Regular cleaning schedule | R&T Chair | Precept - Maintenance | 100% | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
69 | Pedestrian crossing at Whitemans Green | Whitemans Green | Traffic congestion/speed/safety | 2019-07-01 | R&T | Medium | Project | Yes | Medium | WSCC Highways | Discuss with WSCC Highways | R&T Chair | Precept - Major project | 0% | Costs Financial Year 21/22: 30000; 2021 Q1: 1; 2021 Q2: 1; 2021 Q3: 1; 2022 Q4: 1
70 | Traffic light management for speed control | Highways | Reduce traffic speed & increase safety | 2019-07-01 | R&T | Short | Project | Yes | High | WSCC Highways | Discuss with WSCC Highways | R&T Chair | Precept - Major project | 10% | Costs Financial Year 20/21: 2000; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1
71 | New bus shelter at Warden Court | Broad Street | Enhance community asset | 2019-07-01 | R&T | Medium | Project | Yes | Low | WSCC Highways | Discuss with WSCC Highways | R&T Chair | Precept - Minor project | 0% | Costs Financial Year 20/21: 1500; 2020 Q1: 1; 2020 Q2: 1; 2020 Q3: 1; 2021 Q4: 1
72 | Speedwatch | Highways | Reduce traffic speed & increase safety | 2019-07-01 | R&T | On-going | Maintenance | Yes | Medium | Police | Ensure on-going | JB | Precept - Maintenance | 100% | bar: 2019 Q2 to 2020 Q3; 2021 Q1 to 2023 Q3
73 | Road signage for Worsley Memorial recreation ground | Highways | Enhance community asset | 2019-07-01 | R&T | Medium | Project | No
74 | Upgraded cycle ways Cuckfield to Haywards Heath through Blunts Wood | Blunts Wood | Enhance safety | 2019-07-01 | R&T | Long | Project | No
75 | Broad Street cycle lane improvements | Broad Street | Reduce traffic speed & increase safety | 2019-07-01 | R&T | Medium | Project | No